## Sheet1
Test Estimate
Module	No of scenarios	Man days	Type of testing	Dependency
Sanity	8	2	Manual
Farm Creation/Updation/Details display	14	1.5	Manual
Cattle Creation/Updation/Details display	14	1.5	Manual
Gateway Creation/Updation/Details display	14	2	Manual	Release build from Dev Team
AM Creation/Updation/Details display	11	3	manual	Release build from Dev Team
Live/Not Live Status Report for AM/Gateway	8	3	Automation	Release build from Dev Team
Abnormal Orientation Report	7	3	Automation	Release build from Dev Team
Zero AMS Value report	7	3	Automation	Release build from Dev Team
Debounce value Report	10	3	Automation	Release build from Dev Team
Battery Analysis report	11	3	Automation	Release build from Dev Team
Retest and Regression		3	Manaul

## Sheet2
Functions	Available in Requirement Document	Available in Application
Login	no	yes
Associaltion of Gateway and AM	no	yes